## Stage 1
Task | Description | Size
Create a Git repository and make the first commit | Centralize the version of the system received into Corporate Github, with an initial structure for branches, permissions, and working conventions. | S
Run an LLM-based code analysis | Use BMAD Brownfield workflow to map the system architecture, identify modules, dependencies, integrations, and installation risks. | L
Create a technical installation plan | Generate an installation plan with execution order, required components, commands, key considerations, and environment prerequisites. | M
List all external dependencies | Inventory the services, APIs, accounts, and external integrations required for the system to operate correctly. | S
Collect credentials and access for external services | Gather the tokens, keys, logins, accounts, and permissions for all identified external services. | S
Provision the initial infrastructure | Gather the tokens, keys, logins, accounts, and permissions for all identified external services. | M
Configure the server baseline | Install and configure the operating system, web server, PHP, database, extensions, storage, and basic tooling. | M
Prepare the staging environment | Create a separate environment for validation, testing, and fine-tuning before production release. | S
Restore the database in the staging environment | Restore the database in the staging environment | S
Perform the first application installation | Bring the application up in the new environment with the minimum configuration required to run. | L
Validate critical system workflows | Test login, permissions, CRUD operations, uploads, jobs, integrations, and other core business flows. Record errors, limitations, required adjustments, and rework points found during validation. | L
Define the automated deployment model | Choose and configure the deployment flow using GitHub Actions, Docker, scripts, or a simple orchestrator. | S
Set up the deployment pipeline | Implement the automated flow to publish new versions with security and predictable rollback. | M
Define the Lovable usage strategy | Decide whether Lovable will be used only as a development tool or also as an editing layer for the internal team. | S
Plan the frontend/backend separation | Evaluate which parts can be decoupled and which should remain in the current backend. | M
Define the Supabase strategy | Assess which parts of the system can move to Supabase, especially database, auth, and storage. | S